## TaskPlan (hidden)
Projects & Tasks | [8 empty] | Development
# | Type | Team | Priority | Product / Service - EN | Product / Service - JA | Due | Status | Magnitude | Github | Est (人日) | Dev Target | Dev Status | % Complete | Status Bar | Status Comment
P22 | Support | Tech | H | CS Support & Enhancement (ongoing) | CS-UBO サポートと機能強化 | ongoing | 🟢 | XL | 複数 | - | ongoing | 🟩 | - | -
P23 | Support | Tech | H | Hubspot Support (onging) | Hubspot サポート | ongoing | 🟢 | XL | 複数 | - | ongoing | 🟩 | - | -
P02 | Product | Business | VH | Neg Data in CS-UBO (TokyoGov Project) | CS-UBO:ネガティブ記事DBとの連携 | 25/11 | ⚪️ | L | 複数 |  |  | ⏰ | 0% | ⬜️⬜️⬜️⬜️
P03 | Product | Business | VH | Nikkei Article Project (paused til mid Sep) | 日経記事プロジェクト（9月中旬まで一時停止） | 25/11 | 🟢 | XL | 複数 |  |  | ⏰ | 55% | ⏰⏰⬜️⬜️
P34 | Product | Business | VH | Nikke Article "Relationships" Sub project urgent | Nikkei Article "Relationships" Sub project | 25/11 | 🟢 | M | 75 | 15 | 2025-09-08 | 🟩 | 0% | ⬜️⬜️⬜️⬜️
P24 | Solution | Data | VH | "Codex IDR Core" engineering (Beta) | "Codex IDR Core" デザインと開発 (Beta) | 25/10 | 🟢 | XL | 複数 |  | 2025-10-25 | 🟧 | 40% | 🟧🟧⬜️⬜️
P29 | Product | Business | VH | Add parent "overseas" flag to UBO report | UBOレポートに親会社の「海外」フラグを追加 | 25/9 | 🟢 | S | 647 |  | 2025-09-13 | ⏰ | 0% | ⬜️⬜️⬜️⬜️
P30 | Product | Business | VH | Add Search to C-Station API | C-Station APIに検索を追加 | 25/9 | 🟢 | M | 652 | 20 | 2025-09-27 | ⏰ | 0% | ⬜️⬜️⬜️⬜️
P33 | Product | Business | VH | Mini AME batch Utility for Fulfillment team urgent | フルフィルメントチーム向けのAME のバッチユーティリティ | 25/9 | 🟢 | M | 230 | 15 | 2025-09-01 | 🟩 | 0% | ⬜️⬜️⬜️⬜️
P04 | Product | Business | H | New CS-UBO UX (TokyoGov Project) | New CS-UBO UX (TokyoGov Project) | 25/11 | 🟢 | XL | n/a |  |  | 🟩 | 60% | 🟩🟩⬜️⬜️ | Gen-san
P05 | Product | Business | H | Business Status Score (活動実態スコア) | 活動実態スコア | 26/?? | ⚪️ |  |  |  |  | ⬜️ | 0% | ⬜️⬜️⬜️⬜️ | TBD: Design with BusDev
P07 | Product | Business | H | TSR Processing of Rank4 Stats (Monthly) | 顧客が取得した第4順位をTSRに通知 | 25/?? | ⚪️ | M |  |  |  | ⬜️ | 0% | ⬜️⬜️⬜️⬜️ | Neeed more info
P08 | Product | Business | H |  | 年金機構事業所検索システム | 25/11 | 🟢 | L | 129 | 35 |  | 🟩 | 0% | ⬜️⬜️⬜️⬜️ | R&D by data team.
P09 | Product | Business | H | Open Data (Kihonjoho) Monitoring | オープンデータ（基本情報）モニタリング | 26/?? | ⚪️ |  |  |  |  | 🟩 | 0% | ⬜️⬜️⬜️⬜️ | TBD: Design with BusDev
P10 | Product | Business | H | Global Ultimate = Rank4 | 第4順位データの改善：議決権最上位データの利用 | 26/?? | ⚪️ | M |  |  |  | ⬜️ | 0% | ⬜️⬜️⬜️⬜️
P12 | Product | Business | H | Replace AME in CS-UBO | Codex（AMEリプレイス） | 26/01 | ⚪️ | XL | 654, 171 | 100 | 2026-04-01 | ⏰ | 0% | ⬜️⬜️⬜️⬜️ | Waiting for Codex IDR (P24)
P13 | Product | Business | H | Neg Data Monitoring in CS-UBO | モニタリング対象拡大（ネガティブデータ） | 26/?? | ⚪️ | L |  |  |  | ⬜️ | 0% | ⬜️⬜️⬜️⬜️
P17 | Product | Business | H | Supply Chain Risk Analyser (New Product) | サプライチェーンリスク分析ツール（新製品） | 26/?? | ⚪️ | XL |  | 350 |  | ⬜️ | 0% | ⬜️⬜️⬜️⬜️
P26 | Solution | Tech | H | Wire up APIs for Neg Data UI: Teamwork (TokyoGov) | Wire up APIs for Neg Data UI (TokyoGov) | - | ⏸️ | XL |  |  |  | ⏸️ | 25% | ⏸️⬜️⬜️⬜️
P32 | Solution | Tech | H | Neg Data UX: Teamwork App (TokyoGov) | Neg Data UX: Teamwork App (TokyoGov) | - | ⏸️ | XL |  |  |  | ⏸️ | 0% | ⬜️⬜️⬜️⬜️
P14 | Product | Business | M | Codex IDR Mizuho Demo | みずほ銀行でCodexのデモンストレーション | 25/8 | 🟢 | L | 139 |  |  | 🟩 | 40% | 🟩🟩⬜️⬜️
P15 | Product | Business | M | Data Hygiene Product | データ衛生管理製品 | - | ⏸️ | L |  |  |  | ⏸️ | 0% | ⬜️⬜️⬜️⬜️
P16 | Product | Data | M | Demo data for Sales team (Synthetic Data) | 営業チーム向けのデモ用合成データ | - | ⏸️ | L |  |  |  | ⏸️ | 0% | ⬜️⬜️⬜️⬜️
P21 | Product | Tech | M | Backoffice tool | Backoffice アップリケション | - | ⏸️ | XL |  |  |  | ⏸️ | 70% | ⏸️⏸️⏸️⬜️
P18 | Product | Business | L | Compliance Risk Score (TokyoGov V2) | 準拠リスクスコア（東京政府 V2） | 26/?? | ⚪️ |  |  |  |  | ⬜️ | 0% | ⬜️⬜️⬜️⬜️ | Scope TBC
P19 | Product | Business | L | MDM IDR Product | Codex IDR MDM 製品 | - | ⏸️ | XL |  |  |  | ⏸️ | 0% | ⬜️⬜️⬜️⬜️
P20 | Product | Business | L | Enhance UBO reports with extra gBizInfo data | gBizINFO（基本情報、財務情報、特許、届出、補助金、調達等情報取得） | 26/?? | ⚪️ |  |  |  |  | ⬜️ | 0% | ⬜️⬜️⬜️⬜️ | TBD: Design with BusDev
P31 | Product | Business | L | Batch ETC display on-screen in CS | 一括インポート処理完了までの目安時間を表示してほしい | 25/10 | 🟢 | S | 346 |  | 2025-09-27 | ⏰ | 0% | ⬜️⬜️⬜️⬜️ | Scheduled
P35 | [6 empty] | ⚪️ | [5 empty] | 0% | ⬜️⬜️⬜️⬜️
P36 | [6 empty] | ⚪️ | [5 empty] | 0% | ⬜️⬜️⬜️⬜️

## Tracks
Dev Team |  | 2025-08-25 | 2025-09-01 |  |  |  |  | 2025-10-06 |  |  |  | 2025-11-03 |  |  |  | 2025-12-01 |  |  |  |  | 2026-01-05 |  |  |  | 2026-02-02 |  |  |  | 2026-03-02
|  | 2025-08-25 | 2025-09-01 | 2025-09-08 | 2025-09-15 | 2025-09-22 | 2025-09-29 | 2025-10-06 | 2025-10-13 | 2025-10-20 | 2025-10-27 | 2025-11-03 | 2025-11-10 | 2025-11-17 | 2025-11-24 | 2025-12-01 | 2025-12-08 | 2025-12-15 | 2025-12-22 | 2025-12-29 | 2026-01-05 | 2026-01-12 | 2026-01-19 | 2026-01-26 | 2026-02-02 | 2026-02-09 | 2026-02-16 | 2026-02-23 | 2026-03-02 | 2026-03-09 | 2026-03-16
Track 1 - C-Station + Hubspot Support & Enhancements
Track 2
Track 3
Data Team
Track 1 - Data Support & Ad Hoc Requests
Track 2 - Nikkei
Track 3 - IDR
Note on B12: Note that non-Support tracks' titles are just for the current work focus; they are not fixed. サポートのトラック以外のタイトルは現在の作業用であり、固定されたものではありません。
Senshu Ikeda 🔵
GH 676 - CG
Data Counts Dashboard 🔵
GH 000 - KS
TSR Counts 🔵
GH 138 - KS
Neg Data Extracts
for Nikkei 🔵
GH 164 - CG
AME Utility 🔵
GH 230 - CR
Nikkei Entity
Extraction
(Phase 1) 🔵
GH 000 - JH
Codex IDR Core 🔵
GH 000 - WM
Nikkei Entity Relationships 🔵
GH 75 - JH
Codex IDR Mizuho Demo App 🔵
GH 139 - WM
Batch ETC
in CS 🔵
GH 346 - IO
Parent Overseas
Flag 🔵
GH 647 - CM
CS API for Search 🔵
H 652 - CM
People Match
(POC) 🔵
GH 158 - MP
+ Rework ⏳
GH 000 - CG
AME Utility
V2 🔵
GH 000 - CR
Only significant Support tasks will be shown here.
Only significant Support tasks will be shown here.
UBO Overseas Filter
in PF Search🔵
GH 660 - FV
Gen-san CS backend Integration (TokyoGov) 🟢
GH 000 - CG
Usage API for new CS pages
(TokyoGov) 🔵
Codex IDR
TSR Data MVP 🔵
GH 000 - WM
Codex IDR for CS (AME Replace) 🟢
GH 654 - WM/JH
Nikkei Entity Match to MM 🔵
GH 000 - MT/WM
Neg Data Match for CS 🔵
GH 190 - WM
Neg Data Scraping:
Mapping Reiko data 🔵
GH 198 - WM + CG
New TSR data source analysis ⏳
GH 000 - JH/WM
Usage API
design 🔵
Screening API design 🔵
Nikkei Entity Neg Tags (Phase 2) 🔵
GH 000 - JH
Relationships 2:
Link PERSON to ORG 🔵
GH 207 - JH/MT
Usage API stub
to Gen-san 🔵
Neg API stub
to Gen-san 🔵
data-testid for new CS UX 🔵
GH 000 - SG
Nikkei Neg Article Model 🔵
GH 111 - JH
Map auto scraped data to CS 🔵
GH 000 - CG/CM
Screening API for new CS pages
(TokyoGov) 🔵
Neg Data matching in CS 🔵
GH 205 - CG/CM
Neg Data PDFs in Batch 🔵
GH 708 - CG/CM
.Net Patch 🔵
GH 000 - CG/CM
CS Backend Tweaks & Refactor
for speed 🔵
GH 000 - CG
Codex IDR into CS - Dev Integration
(AME replace) ⏳
GH 654 - CG
Extra Relationships extraction🔵
JH
CS Kana search
to half-width katakana
GH 656 - CM
Monitoring in CS API ⏰
GH 702 - CG
Automated Invocing BO 🟢
GH 216 - CR
    Going forward this will mainly be Hori-san and Gen-san.
    今後は主に堀さんと元さんが担当します。

## ref
⚪️ | VH | ⚪️ | Not scheduled | S
🟢 | H | ⏰ | Scheduled | M
🟠 | M | 🟢 | WIP OK | L
🔴 | L | 🟠 | WIP Risk | XL
⏸️ |  | 🔴 | WIP Late
🟣 |  | 🔵 | Done
🔵 |  | ⏳ | Waiting
|  | ⏸️ | Paused
⚪️ Not Started | VH - very high priority
🟢 WIP on track | H - High priority
🟠 WIP at Risk | M - Medium priority
🔴 WIP Running Late | L - Low priority
🟣 Ready for launch
⭕️ On Hold
🔵 Complete